## Sheet1
Use Case | Start Date | End Date | Name
Use case 1: As a user, I want browse questions. | 2014-10-20 | 2014-10-27 | Mujda
Use case 2: As a user, I want to view a question and its answers. | 2014-10-21 | 2014-10-28 | Mujda
Use case 3: As a user, I want to view the replies to a question or answer. | 2014-11-07 | 2014-12-01 | TBD
Use case 4: As an author, I want to make questions. | 2014-10-22 | 2014-10-29 | Edrick
Use case 5: As an author, I want to answer questions by making an answer. | 2014-10-26 | 2014-11-02 | Edrick
Use case 6: As an author, I want to reply to questions and answers to clarify things. | 2014-11-07 | 2014-12-01 | TBD
Use case 7: As an author, I want to attach a picture to my questions or my answers. | 2014-11-07 | 2014-12-01 | TBD
Use case 8: As a sysadmin, I do not want the pictures to be large (> 64kb). | 2014-11-07 | 2014-12-01 | TBD
Use case 9: As a user, I want to sort questions by if they have pictures. | 2014-11-07 | 2014-12-01 | TBD
Use case 10: As a user, I want to sort questions by date or some scoring system. | 2014-10-28 | 2014-11-04 | Byron
Use case 11: As a user, I want to upvote the questions of other users. | 2014-10-27 | 2014-11-03 | Noah
Use case 12: As a user, I want to upvote the answers of other users. | 2014-10-27 | 2014-11-03 | Noah
Use case 13: As a user, I want to see the most upvoted questions and most upvoted answers. | 2014-10-28 | 2014-11-04 | Byron
Use case 14: As a user, I want to see how many answers a question has received. | 2014-10-27 | 2014-11-03 | Byron
Use case 15: As a user, I want to search for questions or answers. | 2014-11-07 | 2014-12-01 | TBD
Use case 16: As an author, I want my device to remember which questions I asked. | 2014-10-31 | 2014-11-07 | Noah
Use case 17: As a user, I want questions and answers that I read or questions and answers that I've indicated I want to read, to be locally cached so I can read them when I am not on the internet. | 2014-10-29 | 2014-11-05 | Shane
Use case 18: As a user, I want to explicitly save some questions as favorites. | 2014-10-29 | 2014-11-05 | Shane
Use case 19: As a user, My favorites and their replies should always be available to me regardless of network connectivity. |  | 2014-12-01 | TBD
Use case 20: As an author, I want to author replies, questions and answers offline. | 2014-11-07 | 2014-12-01 | TBD
Use case 21: As an author, I want to push my replies, questions and answers online once I get connectivity. | 2014-11-07 | 2014-12-01 | TBD
Use case 22: As a user, by default, I should see the most fresh comments. | 2014-11-07 | 2014-12-01 | TBD
Use case 23: As an author, I set my username. | 2014-10-21 | 2014-10-28 | Andy